## Example Issue Tracking
Date Reported | Issue No | Status | Category | Priority | Description | Comments
2026.02.10 | iss01 | Closed | Bug | Critical | metric in timeline (total) different from __perf.csv | done
2026.02.24 | iss02 | Closed | Bug | Low | legend in timeline.html do not having note; add custom text to timeline cfg | done
2026.02.24 | iss03 | Closed | Bug | Low | slow speed when drawing text for video visualization when using custom | done (ignore using draw by font, but use native opencv2 text draw)
2026.03.06 | iss05 | Closed | Bug | Low | current Code can not compared with external exp (results from cls or od models) | done
2026.03.06 | iss06 | Closed | Bug | Critical | incorrect per-frame and per-video resutls (between test code and exp metric calc code) | done
2026.03.09 | iss04 | Open | Bug | Critical | some labels in videos is INCORRECT (need to re-annotate)
2026.03.12 | iss07 | In Progress | Bug | Critical | timeline percentage formula for SKIP method UPDATED. Change to code
2026.03.12 | iss08 | In Progress | Task | Critical | update code to chose the BEST hyper params SET
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low
|  | Open | Bug | Low

## Blank Issue Tracking
Simple Issue Tracking Template
Company
Department
Project Name
Project Manager
Issue Number | Status | Description | Category | Priority | Assignee | Raised By | Date Reported | Date Resolved | Resolution Time | Comments
| Open |  | Bug | Medium

## Key - Do Not Delete
Key - Do Not Delete
Status | Category | Priority
Open | Bug | Low
In Progress | Feature | Medium
Closed | Task | High
| Request | Critical

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.