## Example Issue Tracking
Date Reported | Issue No | Status | Category | Priority | Description | Comments
2026.02.10 | iss01 | Closed | Bug | Critical | metric in timeline (total) different from __perf.csv | done
2026.02.24 | iss02 | Closed | Bug | Low | legend in timeline.html do not having note; add custom text to timeline cfg | done
2026.02.24 | iss03 | Closed | Bug | Low | slow speed when drawing text for video visualization when using custom | done (ignore using draw by font, but use native opencv2 text draw)
2026.03.06 | iss05 | Closed | Bug | Low | current Code can not compared with external exp (results from cls or od models) | done
2026.03.06 | iss06 | Closed | Bug | Critical | incorrect per-frame and per-video resutls (between test code and exp metric calc code) | done
2026.03.09 | iss07 | Closed | Bug | Critical | timeline percentage formula for SKIP method UPDATED. Change to code | done
2026.03.12 | iss08 | Closed | Task | Critical | update code to chose the BEST hyper params SET | done
2026.03.12 | iss09 | Closed | Bug | Low | infer for SKIP method using CACHED infer research from NO_SKIP method | done
2026.03.17 | iss04 | Closed | Bug | Critical | some labels in videos is INCORRECT (need to re-annotate) | done
2026.03.23 | iss10 | Closed | Bug | Low | use pre-computed give wrong elapsed_time (do not use the elapsed_time in no_skip csv for final compute elapsed time) | done
2026.03.27 | iss11 | Closed | Bug | Low | NO_CROP for skip module + update Skip module using FrameDiff | done
2026.04.15 | iss12 | Closed | Bug | Low | update table in (zpaper2) that show metrics having arrow and hightlight best+ second best | done
2026.04.17 | iss13 | Closed | Bug | Low | update all performance tables due to the CHANGES in Ranking Score Calc Fomular | done
2026.04.17 | iss14 | Closed | Bug | Low | update the perf table of "COMPARE to OTHER (TPT method)": run the selected TPT on Test set and report | done
2026.04.21 | iss18 | Closed | Task | Low | update FPS of all table based on pre-computed NoTemp in MainPC
2026.04.17 | iss15 | On Hold | Bug | Low | prepare SOURCE VIDEOS for extract quality analysis frames | done
2026.04.17 | iss17 | On Hold | Task | Low | add heuristic rules for fire/smoke for active motion blocks?
2026.05.12 | iss16 | Open | Task | High | Eager mode: implementation + update report (Hyperparam search on Val + Results on Test set)
2026.05.12 | iss18 | Open | Task | High | Update the text describing the training of BIG Model
2026.05.12 | iss19 | Open | Task | High | RE-check + Update all Paper2 content (to make sure it consistent)
2026.05.12 | iss20 | Open | Task | High | Merge Paper2 Content into Thesis
2026.05.12 | iss21 | Open | Task | Critical | Revise Chapter 1 (Intro) + Chap2 (Literature) + Chap5 (Conclusion + Future) in the Thesis
2026.05.12 | iss22 | Open | Task | Critical | Final review the Thesis before sending out for Committee 's Review
2026.05.12 | iss23 | On Hold | Task | Low | Prepare slides for Thesis Defense

## Runs
run name | target_ds | num_cfg | time_per_cfg_sec | time_per_cfg | total_time _sec | total_time
otp_frame_diff | ufireIndoor_val | 48 | 260 | 0:04:20 | 12480 | 3:28:00
opt_accMotionDet | ufireIndoor_val | 96 |  | 0:00:00 | 0 | 0:00:00
opt_Tpt | ufireIndoor_val | 126 |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00
|  |  |  | 0:00:00 | 0 | 0:00:00